## Portfolio RFI
DATA CENTER PORTFOLIO — REQUEST FOR INFORMATION
Instructions: Please complete one column per project/site in your portfolio. The SAMPLE column is provided as a reference for the level of detail requested. Respond "N/A" where not applicable. Attach supporting documents where referenced. ★ Fields highlighted in yellow were added to address construction checklist gaps (Apr 2026).
Field | SAMPLE PROJECT | Project 1 | Project 2 | Project 3 | Project 4 | Project 5 | Project 6 | Project 7 | Project 8 | Project 9 | Project 10 | Project 11 | Project 12
1. PROJECT OVERVIEW
Project Name | Lone Star Data Campus
Project Codename (if applicable) | Project Maverick
Address / Location Description | 14500 FM 2920, Tomball, TX 77377
GPS Coordinates (Lat, Long) | 30.0972, -95.6163
County, State | Harris County, TX
Nearest Commercial Airport (Code) | IAH (George Bush Intercontinental) — 18 mi
Project Stage | Late-stage development; site control secured, interconnection studies complete
2. POWER & INTERCONNECTION
Grid & Utility
RTO / ISO | ERCOT
Transmission Service Provider / Utility | CenterPoint Energy (T&D); Retail Electric Provider TBD
POI Voltage | 345 kV
Firm/Non-Firm | Firm
Total Requested Data Center Load (MW) | 500 MW
Interconnection Request Submission Date | March 15, 2025
Queue Position / # | LLI-100
Interconnection Request Filed as "Data Center" Use? | Yes - filed specifically as AI / hyperscale data center load
Interconnection Study Status
System Impact Study / Load Studies from TSP/Utility (Complete / In Progress / Not Started) | Steady-State & Stability Studies (and no SSO Study) - approved by Centerpoint, Aug 2025
System Impact Study / Load Studies from RTO/ISO (Complete / In Progress / Not Started) | Complete - approved by ERCOT, Sep 2025
Facilities Study from TSP/Utility (Complete / In Progress / Not Started) | Complete - Centerpoint, Oct 2025
Facilities Study from RTO/ISO (Complete / In Progress / Not Started) | Complete - approved by ERCOT, Nov 2025
Identified Network Upgrades | $12M in transmission upgrades: 1.2 mi 345 kV line extension + new switching station bay
Paid Transmission Security or CIAC ($) | $3.6M paid (30% of estimated upgrade cost)
Outstanding CIAC Amount & Payment Schedule | $8.4M remaining; due upon execution of ESA ($4.2M) and NTP ($4.2M)
Utility-Confirmed Timeline to Complete Upgrades | 12 months from execution of ESA
Agreements & Energization
Interconnection Agreement Executed? (Yes / No) | Yes - executed Jan 2026
ESA / RSA / PPA Executed? (Yes / No) | No - ESA under negotiation; expected execution Q2 2026
Credit/Security Requirements under ESA/RSA/PPA | LOC sized as 2 month prepayment (~$30M) held by Utility for duration of term.
Key ESA / PPA Terms | 15-yr term, take-or-pay at 95% load factor, $/MWh pricing indexed to ERCOT hub
Approved Ramp Schedule | Phase 1 (125 MW): Q4 2027 Phase 2 (125 MW): Q1 2028 Phase 3 (125 MW): Q2 2028 Phase 4 (125 MW): Q3 2028
Outstanding Items to First Power | ESA execution, substation construction, generator procurement & install, utility metering
Outstanding Items to Full Capacity | Centerpoint switching station expansion
Opportunities to Accelerate Energization | Centerpoint has indicated willingness to expedite if ESA executed by Q2 2026. Pre-procurement of transformers underway.
Power Notes | ERCOT interconnection queue position is favorable. No competing large-load applications at this POI.
Utility Reliability History | Yes — CenterPoint reliability data obtained. SAIDI: 82 min/yr; SAIFI: 1.3 interruptions/yr (5-yr avg). No major transmission-level outages at 345 kV POI in past 10 years. Acceptable for Tier III+ operations.
Utility Rate Structure | Analyzed. Demand charge: $8.50/kW-mo; no TOU surcharge for large industrial load > 10 MW. Capacity reservation charge applies at interconnection. Net effective rate ~$0.048/kWh at 95% load factor under draft ESA.
Multiple Utility Feed Options | Yes — evaluated. Primary: CenterPoint 345 kV feed from Tomball substation. Secondary feed option via proposed looped configuration from Cypress Creek substation (3.2 mi). Dual-feed design incorporated in substation specs at full build.
Substation
Existing Electrical Facilities on Site? | No - new customer substation required
Substation Owner | Customer-owned (developer to build, maintain)
Substation Design / Specs | 345 kV / 34.5 kV step-down; GIS configuration; 500 MVA initial, expandable to 800 MVA
Substation Engineering Status | Preliminary design by Burns & McDonnell - 60% complete
Substation Notes | Long-lead transformer ordered (50-wk lead time). Delivery expected Q3 2027.
3. LAND & SITE
Site Characteristics
Total Acreage Under Control | 300 acres
Total Developable / Buildable Acreage | 240 acres
Brownfield or Greenfield | Greenfield
Existing Infrastructure on Site | 3 gas cap wells along eastern boundary; remainder is cleared agricultural land
Site Cleared? | Yes
Current Grade / Topography | Mostly flat (<5%); north parcel has ~10% slope requiring minor cut/fill
Flood Zone Designation (FEMA) | Zone X (minimal flood risk); no portion in 100-yr or 500-yr floodplain
Expansion Opportunities | 3 adjacent undeveloped parcels (100, 200, 30 ac). No discussions with landowners initiated.
Distance from Site to Point of Interconnection | ~1 mile tie-line to 345 kV POI
Adjacent Property Uses | Yes - reviewed. Adjacent north/east: undeveloped agricultural land (compatible). South: single-family residential ~2,500 ft (noise buffer planned). West: industrial/warehouse park (compatible). No incompatible uses identified.
Right-of-Way Requirements for Utilities | Yes - identified. Power: 1.2 mi 345 kV transmission ROW coordinated with CenterPoint. Water: 0.3 mi easement to MUD main on FM 2920. Fiber: Zayo conduit ROW along FM 2920 frontage (confirmed). Gas: existing pipeline easement on eastern boundary. All ROW requirements documented and incorporated in title commitment.
Ingress / Egress & Access Rights — confirmed; easements or access agreements required? (Yes / No) | Yes - confirmed. Site accessed from FM 2920 (state highway) via two proposed drilled curb cuts. No easements required for primary access. Emergency secondary access via northern ranch road. Ingress/egress rights to be formalized in purchase agreement.
Land Ownership & Control
Current Landowner | Tomball Ranch Holdings LLC (Jane Doe, Managing Member)
Exclusivity / Option in Place? | Yes - exclusive option agreement
Option Expiration Date | February 1, 2027
Purchase Price or Lease Terms | $25,000/acre; option to purchase
Title Status | Clear title - title commitment issued by First American Title
Known Liens, Encumbrances, or Easements | Pipeline easement (20 ft) along eastern boundary for existing gas caps. No other liens.
Additional Land Notes
4. DILIGENCE & ENVIRONMENTAL
Site Surveys & Studies
ALTA Survey (Complete / In Progress / Not Started) | Complete - dated Nov 2025
ALTA Notes | Survey shows pipeline easement and 2 utility easements. No encroachments.
Geotechnical Study (Complete / In Progress / Not Started) | Complete - dated Oct 2025
Geotechnical Notes | Soil is sandy loam, suitable for shallow spread footings. No rock or high water table.
Topographic Survey (Complete / In Progress / Not Started) | Complete - dated Sep 2025
Topographic Notes | LiDAR and ground survey. Confirms <5% grade on 240 buildable acres.
Boundary / Legal Survey (Complete / In Progress / Not Started) | Complete - consistent with ALTA
Oversized Load / Heavy Haul Route — state DOT coordination complete and delivery routes confirmed? (Yes / In Progress / N/A) | Yes - complete. TXDOT pre-consultation completed Oct 2025. Oversized transformer and switchgear delivery route identified: I-45 North → SH 99 (Grand Pkwy) → FM 2920. TXDOT confirmed no permit required for current payload specifications. Route flagged for re-review if transformer exceeds 450,000 lbs.
Laydown & Staging Area — acreage available and location identified on site plan? (Yes / No) | Yes - identified. 12-acre laydown/staging area designated on northwest parcel (outside buildable footprint). Location shown on conceptual site plan. Adequate for simultaneous Phase 1 civil and vertical construction. Gravel surface planned for laydown area.
Site Access for Construction Equipment — haul road and entry point confirmed? (Yes / No) | Yes - confirmed. Primary haul road to be constructed along western site boundary connecting FM 2920 to building pad. 40-ft width accommodates dual-direction heavy equipment. Temporary construction entrance with traffic control per Harris County requirements.
Rock Excavation Assessment — geotechnical study addresses rock presence and mitigation? (Yes / No / N/A) | N/A - no rock anticipated. Geotechnical study (Oct 2025) confirms sandy loam to 40 ft depth with no rock encountered in 12 borings. Limestone bedrock not present in this area of Harris County. No rock excavation contingency required.
Environmental
Phase I ESA (Complete / In Progress / Not Started) | Complete - dated Aug 2025
Phase I ESA Notes | 1 REC identified: former above-ground fuel storage near NE corner (since removed)
Phase II ESA Required? (Yes / No) | Yes - limited Phase II for REC area
Phase II ESA (Complete / In Progress / Not Started) | Complete - dated Dec 2025
Phase II ESA Notes | No soil or groundwater contamination detected. NFA letter issued.
Wetlands Delineation (Complete / In Progress / Not Started) | Complete - dated Oct 2025
Wetlands Notes | No jurisdictional wetlands identified on buildable acreage. 2-acre seasonal pond on north parcel excluded from buildable area.
Threatened & Endangered Species Study (Complete / In Progress / Not Started) | Complete - dated Sep 2025
T&E Notes | No critical habitat or listed species observed. USFWS concurrence letter obtained.
Cultural / Archaeological Study (Complete / In Progress / Not Started) | Complete - dated Sep 2025
Cultural Notes | No significant cultural resources found. SHPO clearance received.
Seismic Risk Assessment (Complete / In Progress / Not Started / N/A) | N/A - Not Started (low priority). Site is in Harris County, TX - not in a seismically active zone. USGS hazard map confirms Peak Ground Acceleration <0.05g (Very Low). Seismic design per IBC 2021 Site Class D will apply to structural design but no dedicated seismic risk study required.
Seismic Risk Notes | Seismic design category B per IBC 2021. Standard structural design requirements apply. No special seismic detailing or equipment anchorage beyond code minimum anticipated.
Radon Testing Required & Status — applicable for this region? If yes: (Complete / In Progress / Not Started) | N/A - not required. Radon Zone 3 (EPA designation for Harris County, TX) - predicted average indoor radon < 2 pCi/L. No radon testing required per EPA guidance or local regulation. No below-grade occupied spaces planned in data center design.
Asbestos & Lead Paint Assessment — required for existing structures on site? (Yes / No / N/A) — Status | N/A - Greenfield site. No existing structures on buildable acreage. 3 legacy gas cap wellheads on eastern boundary are surface completions only (no structures). No asbestos or lead paint assessment required.
Groundwater Depth & Quality — assessed in geotechnical study? Depth to water table and quality documented? | Assessed in geotechnical study (Oct 2025). Depth to water table: 18–22 ft below grade (varies seasonally). Groundwater quality: not tested (no contamination risk identified in Phase I). Shallow foundations confirmed viable; no dewatering required for anticipated excavation depths.
Expansive Soil Conditions — identified in geotechnical study; mitigation planned if present? (Yes / No / N/A) | Not identified. Geotechnical study confirms non-expansive sandy loam soils (PI < 15). No shrink-swell potential. Standard foundation design applicable. No mitigation measures required.
Underground Storage Tanks — identified and addressed? (Yes / No / N/A) | Not identified. Phase I ESA (Aug 2025) found no evidence of USTs on buildable acreage. One former above-ground fuel storage tank near NE corner (since removed) was assessed in Phase II - no soil or groundwater impact. NFA letter issued.
USACE Wetlands Permit (404/401) — obtained or exemption confirmed? (Yes / No / N/A) | N/A - no jurisdictional wetlands on buildable acreage. Wetlands delineation (Oct 2025) confirmed no Section 404 jurisdiction on 240 buildable acres. 2-acre seasonal pond on north parcel excluded from development footprint. No USACE permit required. USFWS concurrence obtained.
Flood & Stormwater
Flood Zone Determination / FEMA Map Review | Complete. Zone X - outside of 100-yr and 500-yr floodplain.
Stormwater Management Plan (Complete / In Progress / Not Started) | In Progress - preliminary design complete; detention pond sized for 100-yr event
Stormwater Notes | Harris County Flood Control District review pending. No anticipated issues.
Other Completed Diligence (list any additional) | Traffic Impact Analysis complete. No roadway improvements required for Phase 1.
Diligence Notes / Known Issues | All major diligence items complete or in final stages. No material issues identified.
5. ZONING & PERMITTING
Zoning
Current Zoning Classification | Unincorporated Harris County - no zoning (ETJ of City of Tomball)
Is Current Zoning Compatible with Data Center Use? | Yes - no zoning restrictions apply in unincorporated Harris County
Rezoning or Variance Required? (Yes / No) | No
If Rezoning Required, Status & Expected Timeline | N/A
Special Use Permit or Conditional Use Permit Required? | No
Deed Restrictions or HOA Covenants Affecting Development? | None
Setback / Height / FAR Restrictions | Harris County development standards: 25 ft front setback, 10 ft side, 50 ft max building height (adequate for single-story DC)
Parking Requirements — minimum spaces required; site plan accommodates? (Yes / No / N/A) | N/A - unincorporated Harris County has no minimum parking requirements for industrial/commercial use. Site plan allocates 200 surface spaces (employee + visitor) per operational model. Adequate for projected staffing of ~150 FTE at full build.
Landscape & Screening Requirements — local requirements identified and incorporated in site plan? (Yes / No / N/A) | Minimal requirements. Harris County development standards require 10-ft landscape buffer along FM 2920 frontage. No screening wall required (industrial district context). Landscape plan to include native Texas species per voluntary sustainability commitment. South boundary acoustic barrier will incorporate landscape screening.
Signage Regulations — applicable codes reviewed; any restrictions impacting operations? (Yes / No / N/A) | Minimal restrictions. No municipal sign code applies (unincorporated county). Harris County requires permitted sign for construction site. Facility identification signage to be modest per corporate brand standards. No illuminated signs adjacent to residential boundary.
Future Zoning Changes / Comprehensive Plan Amendments — assessed for risk to project? (Yes / No) | Low risk. Harris County has no active comprehensive plan amendments affecting this area. Tomball ETJ boundary confirmed stable. No proposed annexation or land use reclassification within 1-mile radius per county planning office (confirmed Nov 2025). Texas preemption statutes limit municipal data center restrictions.
Zoning Notes | Unincorporated county location is favorable - no municipal zoning approval process required.
Permitting
Building Permit Status | Not yet submitted - planned for Q2 2026 following site plan completion
Expected Permitting Timeline | ~90 days from submission for initial building permit
Any Known Permitting Risks or Delays? | None identified. Pre-application meeting held with Harris County Permits office - no concerns raised.
Grading / Site Work Permit Status | Not yet submitted; will submit concurrent with building permit
NPDES / Water Discharge Permit Required? (Yes / No) — status and key conditions documented | Yes - required. Site discharges stormwater to Harris County Flood Control District drainage system. TPDES Construction General Permit (CGP) required for land disturbance > 1 acre. Industrial stormwater permit (TPDES Multi-Sector General Permit) required for operational discharge. Filing planned concurrent with construction start (Q1 2027).
Hazardous Materials Storage Permits (fuel, batteries, refrigerants) — AHJ identified and permit requirements documented? (Yes / No) | Yes - identified. Diesel fuel (Phase 1: ~250,000 gal on-site storage across 40 generators). TCEQ Petroleum Storage Tank (PST) registration required for tanks > 1,100 gal. Aboveground Storage Tank (AST) compliance plan to be developed. Lithium-ion battery storage: fire code compliance plan per IFC 2021 Chapter 12 required. AHJ (Harris County Fire Marshal) engaged - pre-application meeting scheduled Q2 2026.
Fire Suppression System Permit Required? (Yes / No) — AHJ and approval pathway identified? | Yes - required. FM-200 / clean agent suppression system planned for electrical rooms; pre-action dry pipe for server halls. Harris County Fire Marshal is AHJ. Permit required prior to system installation. Design-basis documents to be submitted with building permit package. No anticipated issues - standard data center suppression systems well understood by AHJ.
Electrical Permit Requirements with AHJ — documented, including inspection phasing? (Yes / No) | Yes - documented. Harris County Permits Office is AHJ for electrical. Permit required for primary service entrance, distribution switchgear, and generator interconnection. Separate permit for each phase of energization. AHJ confirmed phased inspection process acceptable. Pre-application meeting held Nov 2025.
Utility Connection Permits — identified and timeline mapped? (Yes / No) | Yes - identified and mapped. Required permits: (1) CenterPoint service entrance permit, (2) Harris County MUD #432 water/sewer connection permit, (3) TXDOT driveway/curb cut permit for FM 2920. Timeline for each permit documented in permitting schedule. No anticipated delays.
Road Access Permits (curb cuts, traffic impact study) — submitted or requirements identified? (Yes / In Progress / No) | In Progress. TXDOT driveway permit application submitted Jan 2026 for two curb cuts on FM 2920. Traffic Impact Analysis (TIA) completed - no roadway improvements required for Phase 1 per TIA. Harris County right-of-way permit required for utility crossings on FM 2920 - filing planned Q2 2026.
AHJ Complexity Discussion — pre-application meeting held and review timeline commitments documented? (Yes / No) | Yes - completed. Pre-application meeting held with Harris County Permits Office (Oct 2025). County indicated 60–90 day review timeline for standard data center building permit. No unusual complexity identified. County has processed 2 similar data center permits in past 18 months (precedent established).
Expedited Permitting Options — explored with AHJ? (Yes / No) | Yes - explored. Harris County does not offer formal expedited review program. However, county confirmed availability of concurrent review (civil + building) which compresses overall timeline by ~30 days. Third-party peer review also available - see below.
Third-Party Plan Review Available — evaluated if AHJ timeline is inadequate? (Yes / No / N/A) | Yes - available and under evaluation. Harris County allows registered third-party inspectors for certain trades (mechanical, electrical). If AHJ timeline extends beyond 90 days, will engage third-party structural/MEP reviewer. Two qualified firms identified: Bureau Veritas and Intertek-PSI. Decision to be made at permit submission (Q2 2026).
Air Quality
EPA Attainment / Non-Attainment Status | Marginal Non-Attainment for Ozone (Houston-Galveston-Brazoria 8-hr ozone)
Air Quality Permit Required? (Yes / No) | Yes - TCEQ Permit by Rule (PBR) for backup generators anticipated
Air Permit Status (Obtained / In Progress / Not Started) | Not Started - will file PBR after generator procurement
Expected # of Backup Generators | 40 x 3 MW diesel generators (Phase 1); 80 total at full build
Annual Generator Run-Hour Limitations | TCEQ PBR limits: 100 hrs/yr per unit for non-emergency use; unlimited emergency
Any Emissions Offset Requirements? | No - PBR route avoids New Source Review. If total emissions exceed PBR thresholds, Standard Permit would be required.
Air Quality Notes | Non-attainment designation is common for Houston metro. PBR pathway is well-established for DC backup generators in this region.
Noise
Nearest Noise-Sensitive Receptor (Distance & Type) | ~2,500 ft - single-family residential subdivision to the south
Local Noise Ordinance Limits | Harris County: no specific dB limits for unincorporated areas. City of Tomball (ETJ only): 75 dBA at property line during day, 65 dBA at night.
Noise Mitigation Required? | Preliminary analysis suggests compliance at property line with standard sound attenuated generators. Acoustical barrier may be needed on south boundary.
Noise Study Complete? | Not Started - will commission after final site plan / generator layout
6. FINANCIAL SUMMARY & INCENTIVES
Development Cost Summary
Total Land Cost (actual or estimated) | ~$5.4M ($18K/acre x 300 acres)
Estimated Infrastructure / Site Work Cost | ~$25M (grading, roads, stormwater, water/sewer, substation civil)
Estimated Interconnection / Grid Upgrade Cost | ~$12M (CIAC + customer substation equipment)
Total Estimated Development Spend to Date | ~$8M (land option, studies, engineering, CIAC deposit)
Total Estimated Budget Through First Power | ~$450M (land + infrastructure + Phase 1 DC shell + fit-out + power)
Incentives & Tax
State / Local Tax Incentives Secured or Available? | Texas Chapter 313 successor (Chapter 403) application planned; Harris County offered 10-yr 80% property tax abatement via TIRZ
Sales Tax Exemptions | Texas: DC equipment qualifies for manufacturing exemption on sales tax (SB 1105)
Enterprise Zone or Opportunity Zone? | Qualified Opportunity Zone (Census Tract 2401.02)
Other Incentives or Grants | Greater Houston Partnership workforce training grant ($500K); potential CHIPS Act alignment for AI infrastructure
Job Creation Requirements for Incentives — minimum job count and wage thresholds understood? | Yes - understood. Harris County TIRZ abatement requires minimum 25 FTE jobs at average wage > $75,000/yr within 3 years of certificate of occupancy. Project projects 150 FTE at full build (Phase 4) - well above threshold. Job creation plan to be submitted with TIRZ application (Q2 2026).
Capital Investment Thresholds for Incentives — confirmed and project spend mapped to milestones? | Confirmed. TIRZ abatement requires minimum $200M capital investment within 5 years. Project budget through Phase 1 alone (~$450M) exceeds threshold. Chapter 403 application requires $1B+ investment commitment at full build - confirmed achievable per development plan. Investment milestone schedule mapped to permit issuance and energization dates.
Incentive Application Timeline & Approval Process — mapped and responsibilities assigned? | In Progress. TIRZ application timeline: submit Q2 2026 → Harris County Commissioners Court approval estimated Q4 2026 (2 regular meetings required). Chapter 403 (school district tax limitation): application to Texas Comptroller Q3 2026 → approval Q1 2027. Bracewell LLP engaged to manage both applications. Milestone tracker maintained.
Clawback Provisions & Compliance Requirements — clawback triggers, compliance monitoring obligations, and reporting milestones identified? | Yes - identified and reviewed. TIRZ: clawback triggered if <25 FTE or <$200M investment within 3-yr window. Clawback = prorated return of abated taxes. Chapter 403: recapture if facility ceases operation within agreement term (10 yrs). Compliance reporting: annual certified employment and investment report to Harris County. Legal counsel has reviewed all clawback provisions - no unusual terms.
Utility Rate Incentives or Economic Development Rates — explored with utility? (Yes / No / In Progress) | Yes - in discussion. CenterPoint Economic Development Rate (EDR) program explored. EDR offers reduced transmission and distribution charges for qualifying large industrial loads (> 50 MW). Application to be filed concurrent with ESA execution. Estimated savings: $1.2M–$2.5M/yr at full load. CenterPoint economic development team engaged.
Incentives Notes | Incentive package is competitive vs. peer TX sites. QOZ status provides additional capital gains deferral for investors.
7. COMMUNITY & REGULATORY
Local Government Support / Opposition | Supportive - Harris County Commissioner and Tomball Mayor have expressed public support. Letters of support available.
Community Outreach Conducted? | Yes - 2 community meetings held (Jun & Sep 2025). Positive reception; primary concern was construction traffic.
PR / Public Affairs / Consultant Engagements | Bracewell LLP engaged for state/local government affairs and TCEQ permitting strategy. No active media campaign. No lobbyist registrations filed to date.
Known Opposition (Community Groups, Litigation, etc.) | None - no organized opposition to date
Moratorium or Legislative Risk? | No active moratoriums. TX legislature is broadly supportive of data center development (SB 1105, HB 2543).
Regulatory Notes | TX is among the most favorable regulatory environments for DC development. No state-level permitting beyond TCEQ air quality.
8. WATER & SEWER
Water Provider / Agency | Harris County MUD #432
Water Service Status (Available / Committed / Application Pending) | Committed - will-serve letter issued Nov 2025
Confirmed/Estimated Water Availability | ~400 GPM average
Water Source (Municipal, Well, Reclaimed, etc.) | Municipal surface water (Lake Houston supply via SJRA)
Distance to Water Main | 0.3 miles - 24-inch main on FM 2920
Water Infrastructure Costs (if known) | ~$1.2M for on-site distribution and connection to main
Sewer / Wastewater Provider | Harris County MUD #432 - gravity sewer available
Sewer Capacity Adequate? | Yes - MUD confirmed capacity for projected flows
Water Quality Analysis (Complete / In Progress / Not Started) — mineral content, pH, and hardness tested for cooling system compatibility? | In Progress. Water samples collected from Harris County MUD #432 supply (Jan 2026). Lab analysis pending (results expected Feb 2026). Preliminary MUD data: hardness ~180 mg/L (moderately hard), pH 7.4, TDS ~320 mg/L, chlorides within acceptable range. Cooling system vendor (Evapco) has reviewed MUD quality report - confirms water treatment system design feasible with standard chemical program.
Water Rights / Allocation Permits — required and obtained? (Yes / No / N/A) | N/A - surface water supply. Harris County MUD #432 provides treated municipal surface water (Lake Houston / SJRA). No groundwater use planned; no water rights permits required. MUD will-serve letter issued Nov 2025 confirms adequate allocation for projected 400 GPM average demand.
Industrial Wastewater Permit Required? (Yes / No) — NPDES or local discharge permit status and key conditions | Yes - required. Site discharges to MUD #432 collection system which flows to Harris County MUD WWTP. Industrial discharge permit (Harris County, Harris-Galveston Coastal Subsidence District) not required for data center use. TPDES industrial wastewater permit not anticipated - cooling tower blowdown to be directed to sanitary sewer per MUD agreement. MUD pre-approval obtained for blowdown volumes.
Cooling Tower Water Treatment Requirements — chemical treatment plan and blowdown disposal method identified? | Identified - design in progress. Closed-loop cooling towers require chemical treatment program (scale, corrosion, biocide). Blowdown disposal: to sanitary sewer (MUD pre-approved for projected 50 GPM blowdown at full build). Water treatment vendor (ChemTreat) to be engaged at detailed design phase (Q3 2026). Chemical storage and secondary containment requirements mapped to fire marshal permit package.
Alternative Water Sources Evaluated (wells, reclaimed water)? (Yes / No) | Evaluated - not pursued. Municipal supply (MUD #432) confirmed adequate for projected demand with margin. On-site wells evaluated but not viable (groundwater subsidence district restrictions in Harris County prohibit new groundwater production). Reclaimed water not available within 2 miles of site. Municipal supply is primary and only source.
Water Notes | MUD has ample capacity. No groundwater subsidence district restrictions for surface water use.
9. FIBER & CONNECTIVITY
# of Lit / Dark Fiber Providers Near Site | 3
Fiber Providers & Proximity | Zayo (on FM 2920, adjacent to site), Lumen (0.5 mi), FiberLight (1.2 mi)
Diverse Fiber Path Availability | Yes - 2 diverse entry points achievable via Zayo + Lumen
Nearest Internet Exchange / Meet-Me Room | Equinix HO1 (Houston) - 28 mi; CyrusOne Houston West - 22 mi
Latency to Key Markets (if known) | <2 ms to Houston CBD, <25 ms to Dallas, <45 ms to Atlanta
Last-Mile Fiber Construction Requirements — identified and timeline documented? (Yes / In Progress / No) | Yes - identified. Zayo conduit runs along FM 2920 frontage adjacent to site - on-net connection requires only ~500 ft of on-site conduit (minimal cost). Lumen last-mile: ~0.5 mi aerial build on FM 2920 ROW; Lumen has confirmed 90-day build timeline. FiberLight: 1.2 mi underground build - 120-day timeline per carrier estimate. All timelines compatible with Phase 1 operational target (Q4 2027).
Fiber Provider Construction Timeline — documented for each carrier? (Yes / No) | Yes - documented. Zayo: on-net, 30-day service activation once on-site conduit complete. Lumen: 90-day construction timeline confirmed in writing (Nov 2025 LOI). FiberLight: 120-day estimate, not yet confirmed in writing - follow-up planned Q2 2026. All carrier timelines tracked in project schedule.
Telecommunications ROW Status — right-of-way for last-mile fiber construction confirmed? (Yes / In Progress / No) | Yes - confirmed for primary providers. Zayo: ROW along FM 2920 (existing franchise agreement with Harris County). Lumen: existing aerial ROW on FM 2920 poles. FiberLight: underground - Harris County ROW permit required (standard, 4–6 week process). On-site conduit easement to be included in purchase agreement. No ROW issues anticipated.
Fiber Notes | Zayo conduit runs along FM 2920 frontage - minimal build cost for on-net connection.
10. NATURAL GAS
# of Gas Pipelines On or Near Site | 2
Pipeline Details (Size, Operator, Pressure, Proximity) | Enterprise 16-inch HP lateral (200 psi, on-site eastern boundary); Kinder Morgan 24-inch trunk (800 psi, 0.5 mi north)
Gas Service Available for On-Site Generation? | Yes - Enterprise has confirmed capacity on the 16-inch lateral
Gas Meter & Regulator Requirements — pressure regulation and metering infrastructure identified; connection costs estimated? (Yes / No / In Progress) | Identified. Enterprise 16-inch lateral on eastern boundary operates at 200 psi - requires pressure regulation station to reduce to generator fuel inlet pressure (~15–30 psi). Custody transfer metering and regulator station to be designed by Enterprise and installed at site boundary. Cost estimate: ~$350K (Developer's cost). Design coordination with Enterprise underway.
Gas Service Connection Requirements & Cost Estimate | Estimated at ~$350K for meter/regulator station at site boundary (Enterprise to design and build, Developer to fund). On-site gas distribution piping to generator yard: ~$180K (Developer scope). Total estimated gas infrastructure cost: ~$530K. Enterprise has confirmed cost estimate and construction timeline of 6 months from executed interconnection agreement.
Gas Notes | If future on-site gas generation (turbines or reciprocating engines) is contemplated, gas supply infrastructure is readily available.
11. ON-SITE / BEHIND-THE-METER GENERATION
BTM or On-Site Generation Available or Under Development? | Yes
Generation Type (Solar, Wind, BESS, Gas Turbine, etc.) | Wind
Generator Owner / Developer | Renewable IPP USA LLC
Existing or Under Development? | Under Development
Nameplate Capacity (MW) | 300 MW
Expected COD | Q1 2027
BTM or Physical PPA Available? | Yes - executed PPA with assignment rights to DC successor/assigns
PPA Key Terms (Term, Security Requirements, etc.) | As-generated, floor price PPA. 20-yr term. Islanded wind farm, so BTM delivery is essential for project economics. $30M LOC. Non-IG offtaker acceptable.
Procurement Schedule & Notes | Turbine supply agreement executed with Vestas (V162-6.2 MW units) w. delivery scheduled Q3 2026. Balance-of-plant EPC contract awarded to Mortenson; mobilization planned Q4 2026. Interconnection equipment (collector substation, step-up transformer) ordered w. 42-week lead, delivery Q2 2027. All long-lead items are under contract. No outstanding procurement gating items for Q1 2027 COD.
On-Site Generation Notes | IPP has been commercially cooperative. Wind farm is islanded - as-gen PPA is critical to IPP viability. Gen IX process in progress for additional capacity.
12. SITE PLAN & DESIGN
Conceptual Site Plan Available? (Yes / No) | Yes
Total Planned IT Load (MW) | 400 MW (Phase 1: 100 MW, Phase 2: 100 MW, Phase 3: 100 MW, Phase 4: 100 MW)
Number of Planned Buildings / Phases | 8 buildings in 4 phases
Redundancy Targets (N+1, 2N, etc.) | N+1 mechanical, 2N electrical, 2N+1 utility feeds at full build
Target PUE | < 1.25
Architect / Engineer of Record | HDR Inc. (conceptual); AOR TBD
Site Plan Notes
13. PROCUREMENT & LONG-LEAD ITEMS
Main Power Transformers (Ordered / Lead Time) | Ordered - Siemens 345/34.5 kV, 200 MVA. 50-week lead. Delivery expected Q3 2027.
Medium Voltage Switchgear (Ordered / Lead Time) | Not yet ordered. Budgeted; RFP to be issued Q2 2026. ~36-week lead time.
Backup Generators (Ordered / Lead Time) | Not yet ordered. Caterpillar 3516E (3 MW) budgeted. ~40-week lead. PO planned for Q3 2026.
UPS Systems (Ordered / Lead Time) | Not yet ordered. Evaluating Vertiv / Eaton. ~30-week lead.
Cooling Equipment (Ordered / Lead Time) | Not yet ordered. Budgeted for hybrid air/liquid system. RFP in Q3 2026.
Structural Steel / Precast (Ordered / Lead Time) | Not yet procured. ~20-week lead expected.
Procurement Notes | Transformer is the critical-path long-lead item and has been ordered. Remaining procurement aligns with Phase 1 construction start in Q1 2027.
14. TIMELINE & MILESTONES
Target Construction Start (Phase 1) | Q1 2027
Target First Power / Initial Energization | Q4 2027 (100 MW IT, 125 MW utility)
Target Full Build Completion | Q3 2028 (400 MW IT, 500 MW utility)
Key Milestones & Expected Dates | ESA Execution: Q2 2026 ¦ Building Permit: Q3 2026 ¦ GC NTP: Q4 2026 ¦ Transformer Delivery: Q3 2027 ¦ First Power: Q4 2027 ¦ Phase 2 Energize: Q3 2028
Critical Path Items | ESA execution → transformer delivery → substation energization → building completion
Schedule Risks | ESA negotiation timeline; transformer delivery (ordered, but global supply chain risk); weather delays during hurricane season (Jun-Nov)